## Sheet1
STLC Phase | Task No | Task Description | Assigned To | Planned Completion Date | Actual Completion Date | Deliverable
Requirement Analysis | 1 | Requirement analysis (System Understanding Document study) | Team | 2026-01-09 | 2026-01-09
| 2 | Workflow understanding | Team | 2026-01-19 | 2026-01-19
Test Planning | 3 | Test strategy definition (Manual, Automation, Performance, Security) | Team | 2026-01-19 | 2026-01-19 | Work-Flow
| 4 | Test Plan preparation | Vivek Tiwari | 2026-01-19 | 2026-01-19 | Test Plan
| 5 | Test Plan review and finalization | Gita Mam
Test Case Design | 6 | Test scenario creation | Team | 2026-01-22 | 2026-01-23 | Test Scenario
| 7 | Test case creation | Team | 2026-01-22 | 2026-01-23 | TestCases
| 8 | Test case review | Gita Mam
| 9 | Manual test execution | Team | 2026-01-22 | 2026-01-27 | Test Summary Report
| 10 | Identification of automation-suitable test cases | Vivek & Tilak | 2026-01-23
| 11 | Automation approach and framework planning | Vivek & Tilak | 2026-01-23
| 12 | Performance test scenario identification | Manoj & Vishvjeet | 2026-01-23
Environment Setup | 13 | Security test scenario identification | Manoj & Vishvjeet | 2026-01-23
| 14 | Test environment verification | Vivek & Tilak | 2026-01-26
Test Execution | 15 | Test data preparation | Manoj & Vishvjeet | 2026-01-24
| 16 | Smoke test execution | Team | 2026-01-24
| 17 | Regression test execution | Team | 2026-01-25
| 18 | UI validation testing | Team | 2026-01-25
| 19 | Cross-browser testing execution (local browsers) | Team | 2026-01-26
| 20 | Automation framework setup | Vivek & Tilak | 2026-01-27
| 21 | Automation test script development | Vivek & Tilak | 2026-01-28
| 22 | Automation test script execution (local) | Vivek | 2026-01-29
| 23 | Automation failure analysis | Tilak | 2026-01-29
| 24 | Performance testing execution (basic response & stability checks) | Manoj & Vishvjeet | 2026-01-29
| 25 | Security testing execution (authentication & authorization checks) | Manoj & Vishvjeet | 30-jaunary-2025
| 26 | Defect reporting | Tilak | 30-jaunary-2026
Test Reporting | 27 | Test reporting | Team | 30-jaunary-2027
| 28 | Test Summary Report preparation | Vivek & Tilak | 31-jaunary-2028
| 29 | Test Summary Report submission | Team | 31-jaunary-2028
Test Closure | 30 | Test closure activities | Team | 31-jaunary-2028